## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	Team 48
PROJECT NAME	IOS App
PROJECT MENTOR	Prabhjot Singh Lamba
TEAM MEMBERS	Shaleen Garg
	Shreyash Shriyam
	Ashutosh Ranjan

## Team_Status
TEAM NAME	Team 48
PROJECT NAME	IOS application
PROJECT MENTOR	Vishal Gupta

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 5 (August 31- sept 6)
Learn javascript	Preparation	Shaleen	4		Planned	Codecademy
Learn Javascript	Preparation	Ashutosh	4		Planned	Codecademy
Learn Javascript	Preparation	Shreyash	4		Planned	Codecademy
Role preferences	Coordination	Shaleen	0.5	0.3	Done		0.2	66.6666666667
Discuss application	Coordination	Ashutosh	1	1.5	Ongoing		-0.5	33.3333333333
Develop questions for requirements elicitation	Documentation	Shreyash	5		Planned	Make sure scoping questions are included
Research existing technology	Preparation	Shaleen	2	1.5	Ongoing		0.5	33.3333333333
project plan	Documentation	Ashutosh	2		Planned
project concept	Documentation	Shreyash	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	Shaleen	1	2	Done		-1	50
Status tracker	Documentation	Ashutosh	1		Done
Week 6 (sept 7- sept 13)
Learn Angularjs	Preparation	Ashutosh	6	6	Ongoing		0	0
Team Meeting	Coordination	Shaleen	1	2	Done		-1	50
Status tracker	Documentation	Shreyash	1		Done

Week 8 (sept 14 - sept 20)
Team Meeting	Coordination	Shaleen	1	2	Done		-1	50
Status tracker	Documentation	Shreyash	1	1	Done		0	0
SRS1	Requirements	Ashutosh	8	8	Done
SRS1	Requirements	Shaleen	8	8	Done
SRS1	Requirements	Shreyash	8	8	Done
Learn Angularjs	Preparation	Shaleen	6	6	Ongoing		0	0
Learn Angularjs	Preparation	Shreyash	6	6	Ongoing		0	0
Learn Angularjs	Preparation	Ashutosh	6	6	Ongoing		0	0
Week 9 (sept 21- sept 26)
Team Meeting	Coordination	Shaleen	1	2	Done		-1	50
Status tracker	Documentation	Shreyash	1	1	Done		0	0
Learn Bootstrap	Preparation	Shaleen	6	6	Ongoing		0	0
TestPlan	Design	Ashutosh	8	8	Done
Week 10 (sept 27- Oct 3)
Team Meeting	Coordination	Shaleen	1	2	Done		-1	50
Status tracker	Documentation	Shreyash	1	1	Done		0	0
Coding	Development	Ashutosh	8	8	Ongoing		0	0
Coding	Development	Shaleen	8	8	Ongoing		0	0
Coding	Development	Shreyash	8	8	Ongoing		0	0
Week 11 (Oct 4- Oct 10)
Team Meeting	Coordination	Shaleen	1	2	Done		-1	50
Status tracker	Documentation	Shreyash	1	1	Done		0	0
Release 1	Delivery	Shaleen	3	3	Done		0	0
Release 1	Delivery	Shreyash	3	3	Done		0	0
Release 1	Delivery	Ashutosh	3	3	Done		0	0
Powerpoint Presentation	Delivery	Ashutosh	4	4	Done
Week 12( Oct 11-Oct 17)
Team Meeting	Coordination	Ashutosh	1	2	Done		-1	50
Status tracker	Documentation	Shreyash	1	1	Done		0	0
Studying promises	Preparation	Shaleen	3	3	Done		0	0
Studying promises	Preparation	Shaleen	3	3	Done		0	0
Week 13(Oct 18- Oct 24)
Holidays

Week 14(Oct 24-Oct 30)
Developing app front page	Development	Shaleen	8	6	Done		2	33.3333333333
Developing app front page	Development	Shreyash	6	5	Done		1	20
Design Doc	Documentation	Ashutosh	4	3	Done		1	33.3333333333

Week 15
Improved UI/UX for the application	Development	Shreyash	2	3	Done		-1	33.3333333333
Phonegap build to convert web app to android app	Development	Shaleen	1	1	Done		0	0

Week 16
Dealing with phonegap problems	Development	Ashutosh	3	3	Done		0	0
Dealing with server problems	Testing	Shaleen	2	2	Done		0	0

Week 17
Demo preps for R2	Delivery	Shreyash	1	1	Done		0	0
Updating Status tracker	Documentation	Shaleen	1	1	Done		0	0
Checking all the Docs	Documentation	Ashutosh	1	1	Ongoing		0	0

## Individual_Status
TEAM NAME	48
PROJECT NAME	IOS app for SuperGenie
PROJECT MENTOR	Prabhjot Singh

Actvities	Shaleen Garg		Ashutosh Ranjan		Shreyash Shriyam		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 5 (August 31- sept 6)
Learn Angular JS	10 hrs	8 hrs	10 hrs	9 hrs	10 hrs	9 hrs	30 hrs	26 hrs

Week 6 (sept 7- sept 13)
Learn IONIC Framework	3hrs	2 hrs	3 hrs	4 hrs	3 hrs	3 hrs	9 hrs	9hrs

Week 8 (sept 14 - sept 20)
Basic Implementation	5hrs	5 hrs	5hrs	5 hrs	5hrs	5 hrs	15 hrs	15 hrs

Week 9 (sept 21- sept 26)
Wrote code for getting the bot functional.	5hrs	5 hrs	5hrs	5 hrs	5hrs	5 hrs	15 hrs	15 hrs

Week 10 (sept 27- oct 3)
Added bootstrap.	3hrs	3hrs	3 hrs	3hrs	3 hrs	3 hrs	9 hrs	9hrs
Made the “view” look better.	5hrs	5 hrs	5hrs	5 hrs	5hrs	5 hrs	15 hrs	15 hrs

Week 11 (Oct 3- Oct 9)
Powerpoint presentation.	3hrs	3hrs	3 hrs	3hrs	3 hrs	3 hrs	9 hrs	9hrs
Preparing demo for R1.	5hrs	5 hrs	5hrs	5 hrs	5hrs	5 hrs	15 hrs	15 hrs
Final touches before R1.	3hrs	3hrs	3 hrs	3hrs	3 hrs	3 hrs	9 hrs	9hrs

Week 12 (Oct 10- Oct 16)
Searching techniques to add rooms.	3hrs	3hrs	3 hrs	3hrs	3 hrs	3 hrs	9 hrs	9hrs
Studying “promises” in angularjs.	3hrs	3hrs	3 hrs	3hrs	3 hrs	3 hrs	9 hrs	9hrs

Week 13 (Oct 17- Oct 23)
Holidays	0hrs	0hrs	0hrs	0hrs	0hrs	0hrs	0hrs	0hrs

Week 14(Oct 24-Oct 30)
Developing app front page	8 hrs	6 hrs	6 hrs	5 hrs	4 hrs	3 hrs	18 hrs	14 hrs
Developing app front page
Design Doc

Week 15 (Nov 1-Nov 7)
Imroved the app front page	4 hrs	3 hrs	4 hrs	2 hrs	4 hrs	2 hrs	12 hrs	7 hrs
used phonegap to convert website into app

Week 16 (Nov 8- Nov 15)
Final touches and dealing with server probs	6 hrs	4 hrs	6 hrs	3 hrs	6 hrs	3 hrs	18 hrs	10 hrs			0	0
Preparing demo for R2						0	0
						0	0
						0	0
Week 17 (Nov 16- Nov 23)						#VALUE!	#VALUE!
Updating status tracker	0hrs	0hrs	1 hrs	1 hrs	0hrs	0hrs	1 hrs	1 hrs			0	0
Checking all the docs						0	0
						0	0
						#VALUE!	#VALUE!
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0